AQUALEO · build — THE PANDIT

# Development Plan v2.0

Detailed design and development plan covering Requirement Specifications v2.0, Addendum A and Addendum B. Supersedes Development Plan v1.1.

| Document | Development Plan v2.0 |
| --- | --- |
| Reads with | Requirement Specifications v2.0 · Addendum A · Addendum B · Architecture v1.1 + v2.0 Delta |
| Audience | Engineering leads, AI orchestrator agent, PMO |
| Status | Draft for review |
| Date | September 2026 |

# 1. Delivery structure

Five parallel tracks with stage gates. Each track maps 1:1 to a subagent in the AI Agent Prompts document.

| Track | Scope | Owner subagent |
| --- | --- | --- |
| T1 Panchang Core | PCS, cache, festival rule engine, muhurat, reminders, accuracy harness | panchang-engine |
| T2 Platform | Identity, Vault, gateway/entitlements, subscriptions, CMS, notifications, PDF, AI, infra/CI | platform-backend |
| T3 Commerce Core | Stripe Connect, KYC, ledger, commission, payouts, disputes, tax, multi-currency | commerce-core |
| T4 Marketplaces | Pandit Services module (A) and Pooja Items module (B) | marketplace-a, marketplace-b |
| T5 Clients | Mobile, web, admin console, provider/seller portal | clients |
| QA / Compliance | Accuracy dataset, contract tests, security review, store-compliance review | qa-compliance |

# 2. Stages and gates

| Stage | Weeks (est.) | Deliverables | Exit gate |
| --- | --- | --- | --- |
| S0 Foundations | 1–2 | Monorepo, IaC, CI, ADRs for open decisions (mobile stack, video SDK, §A19 defaults), OpenAPI skeleton, data model migrations v1 | ADRs signed; CI green with harness stub |
| S1 Panchang truth | 3–8 | PCS complete incl. all edge cases; cache + warmer; accuracy harness ≥500 reference days / ≥10 locations; festival DSL + 40 major rules | HARD GATE: 100% on tithi/nakshatra at sunrise; ±1 min sunrise/sunset |
| S2 Core product MVP | 6–14 | Auth, profiles, Vault, day/month views, festivals, notes/bookmarks, basic reminders, subscriptions + entitlements, CMS, basic PDF | E2E on 3 clients; ≤2 s p95 day view |
| S3 Commerce Core | 8–14 (parallel) | Connect onboarding, KYC adapter, ledger, commission config, payout scheduler, dispute workflow, Stripe Tax, webhook processors | All §A6.2 money flows pass in sandbox; reconciliation balances |
| S4 Pandit Services MVP | 12–20 | Provider onboarding/approval, taxonomy, travel/geo, availability, booking FSM, quote engine, messaging with masking, reviews, transactional emails, admin consoles | No double-booking under concurrency test; policy snapshot enforced; ops console complete |
| S5 Pooja Items MVP | 14–20 (parallel) | Shopify headless, samagri→cart, order ingest, seller splits via Commerce Core | Order → payout traced end-to-end |
| S6 Phase-2 features | 20–28 | Live video, full tithi reminders, muhurat finder, vrat tracker, widgets, HD PDF, ranking v2, standing automation | SLOs met; video join success ≥98% in staging |
| S7 Launch hardening | 26–30 | Commercial Swiss Ephemeris licence in prod build, pen test, store-compliance review, data residency, runbooks | HARD GATE: licence secured; compliance sign-off |

Week estimates assume parallel tracks and are planning figures, not commitments.

# 3. Epic breakdown per track

## T1 Panchang Core

PCS-1 Ephemeris wrapper, Lahiri ayanamsa with override, sunrise/sunset/moonrise/moonset

PCS-2 Five angas as interval arrays; sunrise-to-sunrise day; hoursFromSunrise

PCS-3 Edge cases: kshaya/vriddhi tithi, adhika/kshaya maas, polar fallback, DST mid-tithi

PCS-4 Derived windows: Rahu Kalam, Yamaganda, Gulika, Abhijit, Dur Muhurat, Varjyam, Amrit Kalam, Brahma Muhurat, Nishita, Choghadiya, Hora, Gowri

PCS-5 Cache (Postgres partitioned + Redis), grid keys, per-key lock, warmer with pre-festival widening

PCS-6 Festival Rule DSL, resolver, 40 major rules + recurring cycles, regional overrides

PCS-7 Muhurat scoring with explanation trace

PCS-8 Reminder recurrence resolver (Gregorian, weekday, tithi, nakshatra, lunar/solar month, festivalRef) with idempotent fire keys

PCS-9 Accuracy harness as required CI check

## T2 Platform

PLT-1 Identity (OIDC Google/Apple, OTP, guest→upgrade), RBAC, audit trail

PLT-2 Profiles, locations, family members

PLT-3 Vault service: separate DB, KMS envelope encryption, access log, region pinning

PLT-4 Gateway middleware: auth, entitlement, rate limit, tracing

PLT-5 Subscriptions: IAP / Play / Stripe-web reconciliation; entitlement cache

PLT-6 CMS with Draft→Review→Published→Archived, ContentVersion, region tags, flag queue

PLT-7 Notifications: push/email/in-app/SMS, quiet hours, templates

PLT-8 PDF workers (Playwright, 300 DPI) + object storage signed URLs

PLT-9 AI Guidance: RAG over Published content + Panchang tools + disclaimer + metering

PLT-10 Search; GDPR export/delete; Terraform; CI/CD; observability

## T3 Commerce Core

COM-1 Provider account + Stripe Connect Express onboarding

COM-2 KYC adapter (Stripe Identity default; pluggable); artefacts to Vault

COM-3 Double-entry ledger + journal from webhooks

COM-4 Commission & fee config; pass-through policy

COM-5 Escrow: manual-capture PaymentIntents; capture on confirm; release after holdback

COM-6 Payout scheduler, on-demand payout, statements, tax documents

COM-7 Refund engine driven by policy snapshots

COM-8 Dispute workflow; payout freeze; evidence bundle

COM-9 Standing score

COM-10 Stripe Tax; multi-currency; FX; nightly reconciliation

## T4 Pandit Services

MPA-1 Pandit profile, approval queue, badges

MPA-2 ServiceType taxonomy admin, linked to festival/muhurat IDs

MPA-3 TravelPolicy + PostGIS distance + fee models

MPA-4 Availability engine, calendar sync, no double-booking

MPA-5 Booking FSM, atomic slot + PaymentIntent, response-window expiry

MPA-6 Quote engine + policy snapshot

MPA-7 Search/filter/sort ≤1 s; explainable ranking

MPA-8 Messaging with PII masking, leak detection, pre-booking Q&A rate limits

MPA-9 Two-way verified reviews with delayed reveal; moderation

MPA-10 Video Session adapter, waiting room, join log, consented recording

MPA-11 Transactional notifications (§A10)

MPA-12 Admin: booking & dispute console, payout management, fraud queues

## T4 Pooja Items

MPB-1 Shopify Storefront integration (catalog, cart, hosted checkout)

MPB-2 SamagriList → cart mapping

MPB-3 Order/fulfilment webhook ingest

MPB-4 Seller onboarding and splits via Commerce Core

MPB-5 Order tracking surfaces; disputes via Commerce Core

## T5 Clients

CLI-1 Design system + shared API client from OpenAPI (mocks first)

CLI-2 Day/week/month/year views; 24-plus display; offline month bundles

CLI-3 Festivals, notes, bookmarks, reminders, family calendar

CLI-4 Subscription purchase flows (IAP/Play/Stripe-web)

CLI-5 Pandit discovery, profile, booking, messaging, video

CLI-6 Pooja Items storefront overlay

CLI-7 Provider/Seller portal; admin console

CLI-8 Widgets / lock-screen

# 4. Testing & quality strategy

| Layer | Approach |
| --- | --- |
| PCS | Golden-dataset harness (required CI check); property tests (tithi monotonic, 30 tithis per lunation, adhika detection for known years) |
| Rules | Snapshot tests of resolved festival dates per region versus published Panchang |
| Money | Stripe test-clock scenarios for every §A6.2 row; ledger balances to zero |
| Booking | Concurrency: 50 parallel requests for one slot → exactly 1 Confirmed |
| Clients | E2E (Detox/Playwright); offline-mode tests; entitlement bypass attempts must return 403 |
| Security | Vault access-log audit; PII masking tests; webhook forgery tests |
| Compliance | IAP separation, licence flag, legal acceptance logs, GDPR export/delete incl. bookings & messages |

# 5. Open decisions requiring sign-off (defaults assumed)

| # | Decision | Default assumed | Needed before |
| --- | --- | --- | --- |
| 1 | Commission take-rate; applies to travel/samagri? | Flat % on service fee only; pass-through | S3 |
| 2 | Inner cancellation tiers | 50% inside 30 d; 0% inside 48 h | S4 |
| 3 | Payout holdback | 48 h | S3 |
| 4 | Background-check depth per market | Max permitted in US/UK; disclosed | S4 |
| 5 | Recording of remote sessions | Off by default; both-party opt-in | S6 |
| 6 | Video SDK vendor | LiveKit (evaluate Agora/Twilio) | S6 |
| 7 | Gold-tier marketplace perks | Reduced fee + priority dispute support | S4 |
| 8 | Provider listing fee | None | S4 |
| 9 | Mobile stack | Decide at S0 (ADR-001) | S0 |

# 6. Risks & mitigations (delta)

| Risk | Mitigation |
| --- | --- |
| Marketplace tracks starve the Panchang core of attention | S1 hard gate before any marketplace UI ships; harness is a required check |
| Payment co-mingling causes store rejection | Lint/contract rule: three rails; qa-compliance reviews every payment surface |
| Double-booking under load | Row-level locks + idempotent PaymentIntent; concurrency test in CI |
| Ledger drift vs Stripe | Nightly reconciliation; alert on non-zero variance |
| Licence gate missed | SWISSEPH_LICENSE_MODE enforced in prod pipeline; S7 gate |